## POA&M
***** CONTROLLED UNCLASSIFIED INFORMATION *****
Date Exported: | [10 empty] | System Type: |  |  |  | OMB Project ID:
Exported By:
CC/S/A/FA: | [10 empty] | POC Name:
System / Project Name: | [10 empty] | POC Phone: |  |  |  | Security Costs:
DoW IT Registration No: | [10 empty] | POC E-Mail:
| POA&M Item ID | Control Vulnerability Description | Controls / APs | Security Checks | POA&M Status | POA&M Scheduled Completion Date | POA&M Requested Risk Accepted Expiration Date | POA&M Completion Date | Milestone ID | Milestone Description | Milestone Status | Milestone Status Comments | Milestone Scheduled Completion Date | Milestone Completion Date | Identification Source | Identification Source Details | Office/Org | Resources Required | Comments | Raw Severity | Devices Affected | Mitigations (in-house and in conjunction with the Navy CSSP) | Predisposing Conditions | Severity | Relevance of Threat | Threat Description | Likelihood | Impact | Impact Description | Residual Risk Level | Recommendations | Resulting Residual Risk after Proposed Mitigations

## Example
***** CONTROLLED UNCLASSIFIED INFORMATION *****
Date Exported: | [10 empty] | System Type: |  |  | OMB Project ID:
Exported By:
CC/S/A/FA: | [10 empty] | POC Name:
System / Project Name: | [10 empty] | POC Phone: |  |  | Security Costs:
DoW IT Registration No: | [10 empty] | POC E-Mail:
| POA&M Item ID | Control Vulnerability Description | Controls / APs | Security Checks | POA&M Status | POA&M Scheduled Completion Date | POA&M Requested Risk Accepted Expiration Date | POA&M Completion Date | Milestone ID | Milestone Description | Milestone Status | Milestone Status Comments | Milestone Scheduled Completion Date | Milestone Completion Date | Identification Source | Identification Source Details | Office/Org | Resources Required | Comments | Raw Severity | Devices Affected | Mitigations (in-house and in conjunction with the Navy CSSP) | Predisposing Conditions | Severity | Relevance of Threat | Threat Description | Likelihood | Impact | Impact Description | Residual Risk Level | Recommendations | Resulting Residual Risk after Proposed Mitigations
| 1 | Description that explains the identified vulnerability and any other pertinent information. | AC-1 | SV-18394r2_rule | Ongoing | 2025-11-23 |  |  | 1 | Implement Procedure A | Completed | Sample comments explaining the selected milestone status. | 2025-11-05 |  | Vulnerability Management | Narrative description of how this vulnerability was discovered (annual review, automated scan, etc.) | DoD, John Smith, 7033775472, smith_john@email.com | Resources required to correct the identified vulnerability. | Description of any relevant information not captured by the other fields. | High | Identify affected devices. | Description of the mitigations in place (if any) to counter this vulnerability. | Description of the predisposing conditions (if any). | High | High | Description of the identified theat(s). | High | High | Description of magnitude of potential harm from the exploitation of this vulnerability. | High | Summary of the recommended actions that will further address/reduce the risk of this vulnerability. | Moderate
[9 empty] | 2 | Implement Procedure B | In Progress | Sample text. | 2025-11-15
[9 empty] | 3 | Implement Procedure C | Open | Sample text. | 2025-11-23
| 2 | Description that explains the identified vulnerability and any other pertinent information. | SA-1.4 | SV-40098r2_rule | Risk Accepted | [9 empty] | Vulnerability Management | Narrative description of how this vulnerability was discovered (annual review, automated scan, etc.) | DoD | Resources required to correct the identified vulnerability. | Description of any relevant information not captured by the other fields. | Low | Identify affected devices. | Description of the mitigations in place (if any) to counter this vulnerability. | Description of the predisposing conditions (if any). | Very Low | Low | Description of the identified theat(s). | Very Low | Moderate | Description of magnitude of potential harm from the exploitation of this vulnerability. | Low | Summary of the recommended actions that will further address/reduce the risk of this vulnerability. | Very Low
| 3 | Description that explains the identified vulnerability and any other pertinent information. |  |  | Completed | 2025-10-25 |  | 2025-11-03 |  | Sample milestone description. | Completed | Sample text. | 2025-10-20 | 2025-11-03 | Operational; Risk Assessment Findings | Narrative description of how this vulnerability was discovered (annual review, automated scan, etc.) | Example Program Management Office | Resources required to correct the identified vulnerability. | Description of any relevant information not captured by the other fields. | Low | Identify affected devices. | Description of the mitigations in place (if any) to counter this vulnerability. | Description of the predisposing conditions (if any). | High | Moderate | Description of the identified theat(s). | Moderate | High | Description of magnitude of potential harm from the exploitation of this vulnerability. | Moderate | Summary of the recommended actions that will further address/reduce the risk of this vulnerability. | Low
| 4 | Description that explains the identified vulnerability and any other pertinent information. | AT-2 |  | Risk Accepted |  | 2025-12-31 | [7 empty] | Compliance Gaps; Data Protection and Privacy; Risk Assessment Findings | Narrative description of how this vulnerability was discovered (annual review, automated scan, etc.) | DoD | Resources required to correct the identified vulnerability. | Description of any relevant information not captured by the other fields. | Low | Identify affected devices. | Description of the mitigations in place (if any) to counter this vulnerability. | Description of the predisposing conditions (if any). | Very Low | Low | Description of the identified theat(s). | Very Low | Moderate | Description of magnitude of potential harm from the exploitation of this vulnerability. | Low | Summary of the recommended actions that will further address/reduce the risk of this vulnerability. | Very Low

## Instructions
POA&M Template Instructions | Combination of Vulnerability Severity/Predisposing Condition Pervasiveness and Threat Relevance
1. Enter valid information into the fields on the POA&M Template. | Relevance of Threat | Vulnerability Severity/Predisposing Condition Pervasiveness
2. The "POA&M Item ID" and any "Milestone IDs" are automatically generated by eMASS after the POA&M Item is successfully imported. No user action is required to complete or update and therefore these columns can be treated as read-only.
3. Control Vulnerability Description - Describe the vulnerability associated with each non-compliant security control. This should be the test tool defined vulnerability description. |  | Very Low | Low | Moderate | High | Very High
4. Controls / APs - List the affected security controls / assessment procedures. | Very High | Very Low | Low | Moderate | High | Very High
5. Security Checks - NIST -53Rev 4 Assessment Procedure, STIG / SRG Vulnerability ID, or ACAS Plugin ID (Do not leave this field blank). | High | Very Low | Low | Moderate | High | Very High
6. Status - N/A, Ongoing, Risk Accepted, Completed. Note: Risk Accepted should only be selected once the AO has accepted the risk. | Moderate | Very Low | Low | Moderate | Moderate | High
7. POA&M Scheduled Completion Date - When does the program anticipate remediating the vulnerability. | Low | Very Low | Low | Low | Low | Moderate
8. POA&M Requested Risk Accepted Expiration Date - Identifies a POA&M Item that requires a shorter-term acceptance of risk. The field should be left blank for cases where a resolution is not possible/feasible and thus long-term risk acceptance is required. | Very Low | Very Low | Very Low | Low | Low | Low
9. POA&M Completion Date - Date that the overall plan was resolved (where "Status" = 'Completed').
10. Milestone Description - Description of the specific milestone. | Combination of Likelihood and Impact
11. Milestone Status -The current state of the specific milestone. | Likelihood (Threat Event Occurs and Results in Adverse Impact) | Impact
12. Milestone Status Comments - Optional comments to support or describe the selected milestone status.
13. Milestone Scheduled Completion Date - When does the program anticipate the resolution of the specific milestone. |  | Very Low | Low | Moderate | High | Very High
14. Milestone Completion Date - Date that the specific milestone was resolved (where "Milestone Status" = 'Completed') | Very High | Very Low | Low | Moderate | High | Very High
15. Identification Source - Select the most appropriate source or other category tag for this vulnerability. | High | Very Low | Low | Moderate | High | Very High
16. Identification Source Details - Provide any additional information as necessary related to the discovery method of this vulnerability.
17. Office/Org - When entering Office/Org, enter Organization, First Name Last Name, Phone Number, Email. At a minimum, the Office/Org must be defined for each POA&M Item. If multiple fields are entered, ensure each field is separated by a comma. Do not separate first and last name with a comma. | Moderate | Very Low | Low | Moderate | Moderate | High
18. Resources Required - What resources are required in order to address the vulnerability. | Low | Very Low | Low | Low | Low | Moderate
19. Comments - Add any additional feedback not covered in specific POA&M fields. | Very Low | Very Low | Very Low | Low | Low | Low
20. Raw Severity - Record the initial severity as identified by the test methodology. Failed 800-53 R4 assessment procedures without clearly identified severity/impact should assume the high watermark of the C-I-A impact to the parent control (e.g., a failed assessment procedure affecting Integrity for a system with Moderate impact to Integrity would assume a Moderate raw test result).
21. Devices Affected - List affected devices (by hostname). Devices of varying configuration and purpose may be impacted differently by a vulnerability and should be listed as separate line items in the RAR for risk analysis.
22. Mitigations (in-house and in conjunction with the Navy CSSP) - Technical mitigation(s) that are present and further reduce the initial severity. Enter "none" if there is no applied mitigation that decreases severity/pervasiveness. Mitigations directly address the vulnerability and are compensating countermeasures. (e.g. custom HBSS signature preventing execution of a specific vulnerable .dll on a system, failover or redundancy addressing DoS conditions) in accordance with the Navy Certifying Authority Mitigation Methodology memorandum dated 01 Oct 2014.
23. Predisposing Conditions - Predisposing condition(s) that affect the raw severity value. Enter "none" if there is no relevant condition that increases or decreases severity/pervasiveness. A predisposing condition is a condition existing within an organization, a mission or business process, enterprise architecture, information system/PIT, or environment of operation, which affects (i.e., increases or decreases) the likelihood that threat events, once initiated, result in adverse impacts. (Department of Defense (DoD) Cybersecurity Risk Assessment Guide, page 4)
24. Severity - Vulnerability severity is derived from the raw vulnerability, adjusted by relevant predisposing conditions and mitigations. If there are no relevant predisposing conditions or applied technical mitigation(s), the severity aligns with the raw test results. Identify the severity or pervasiveness as one of the following: Very Low (VL), Low (L), Moderate (M), High (H), or Very High (VH).
25. Relevance of Threat - Determine whether the threat source is adversarial or non-adversarial in nature. Adversarial threat source: the DoD Risk Assessment Guide notes the significance of the "advanced persistent threat". Vulnerabilities of an adversarial nature must reflect a minimum of "High" in this field. Non-adversarial threat source: This value takes into consideration multiple NIST SP 800-30 risk factors, such as the range of effects, extent of resources affected and whether any critical resources are affected; Relevance of Threat descriptions from the NIST SP 800-30 are included in the "Assessment Tables" tab in Table D-2. Identify the relevance of threat as one of the following: Very Low (VL) - minimal effects involving few, if any resources, involving no critical resources, Low (L) - limited effects involving some resources, involving no critical resources, Moderate (M) - wide-ranging effects involving a significant portion of resources, including some critical resources, High (H) - extensive effects involving most resources, including many critical resources, Very High (VH) - sweeping effects involving almost all resources
30
26. Likelihood - This value is automatically calculated as a result of "Severity" and "Relevance of Threat". DO NOT CHANGE THE RECOMMENDED VALUE. Determine the likelihood a threat event will be initiated or occur and result in adverse impacts (see Table 5 on the RMF KS page "Model for Assessing Residual Risk Level for Non-Compliant Security Controls" for likelihood values). Likelihood is a combination of likelihood of attack initiation / occurrence and likelihood that initiated attack succeeds or the threat even results in adverse impact. If resource constraints allow, risk assessors may reference NIST SP 800-30 for guidance on determining this value (i.e., could use another 5x5 matrix to plot the two factors and determine the overall likelihood). However, as the likelihood is summarized in this model, risk assessors assign a value by comparing the results of "Severity" with the "Relevance of Threat." The factors from these two columns are plotted on a 5x5 matrix, and the intersection on the matrix indicates the value for likelihood. Identify the likelihood as one of the following: Very Low (VL), Low (L), Moderate (M), High (H), or Very High (VH).
27. Impact - Determine the adverse impact (i.e., potential harm to organizational operations, organizational assets, individuals, other organizations, or the Nation) from the threat event. Risk assessors may consider the Concept of Operations, system description, User Representative input, etc. (See Table 6 on the RMF KS page "Model for Assessing Residual Risk Level for Non-Compliant Security Controls" for descriptions of the values assigned to impact. Identify the impact as one of the following: Very Low (VL), Low (L), Moderate (M), High (H), or Very High (VH).
28. Impact Description - Describe the impact to the mission, information system, organization and organizational assets, other organizations, individuals, or the Nation as a result of exploitation of the vulnerability/weakness. Note: If adequate justification is not provided, the Impact will default to a minimum of "High".
29. Residual Risk Level - This value is automatically calculated as a result of "Likelihood" and "Impact" fields. DO NOT CHANGE THE RECOMMENDED VALUE. Determine the level of risk as a combination of likelihood and impact (see Table 7 on the RMF KS page "Model for Assessing Residual Risk Level for Non-Compliant Security Controls" for descriptions of values assigned to risk). Identify the risk as one of the following: Very Low (VL), Low (L), Moderate (M), High (H), or Very High (VH).
30. Recommendations - The PM/SM lists the recommendations addressing actions that will at a minimum reduce the High and Very High Risk non-compliant security controls to a Moderate Risk.
31. Resulting Residual Risk after Proposed Mitigations - Indicate the risk level expected after the proposed mitigations are implemented.
Situational Awareness
1. Enter valid information into the fields on the POA&M Template.
2. The POA&M Item ID and any Milestone IDs are automatically generated by eMASS after the POA&M Item is successfully imported. No user action is required to complete or update and therefore these columns can be treated as read-only.
3. Do not delete columns/sheets, delete the classification label, or add additional columns. Doing so may have a negative impact on the ability for eMASS to ingest the template.
4. To import a system-level POA&M Item, the "Controls / APs field" must be left blank.
5. To import a control / assessment procedure-level POA&M Item, enter the appropriate control / assessment procedure acronym(s) (e.g., AC-3) into the "Controls / APs" field.
6. When listing multiple control / AP associations for a specific POA&M Item, separate each association by a semicolon.
7. When populating the "Office/Org" field, enter Organization, First Name Last Name, Phone Number, Email. At a minimum, the "Office/Org" must be defined for each POA&M Item. If multiple fields are entered, ensure each field is separated by a comma. Do not separate first and last name with a comma.
8. "Security Checks" (optional field) can be populated with DISA Security Technical Implementation Guide (STIG) rules (i.e. SV-40098r2_rule), USCYBERCOM IAVM IDs, or Nessus Plugin IDs.
9. When listing multiple Security Checks for a specific POA&M Item, separate each Security Check by a semicolon.
10. For POA&M Items with a "Status" of 'Ongoing', the "Status", "Scheduled Completion Date", "Office/Organization", "Vulnerability Description", "Resources Required", and "Identification Source" fields are required. All ongoing POA&M Items must have at least one milestone.
11. For POA&M Items with a "Status" of 'Risk Accepted', the "Status", "Office/Organization", "Vulnerability Description", "Resources Required", "Comments", and "Identification Source" fields are required. Milestones are not allowed for risk accepted POA&M Items.
12. For POA&M Items with a "Status" of 'Completed', the "Status", "Scheduled Completion Date", "Office/Organization", "Vulnerability Description", "Resources Required", "Comments", and "Identification Source" fields are required. All completed POA&M Items must have at least one milestone and all milestones must have a "Milestone Status" of 'Completed' or 'Archived'.
13. For POA&M Items with a "Status" of 'Ongoing', the "Scheduled Completion Date" should reflect the overall date that the entire plan is expected to be resolved.
14. For POA&M Items with a "Status" of 'Risk Accepted', the "POA&M Requested Risk Accepted Expiration Date" is an optional field that can be used to identify a POA&M Item that requires a shorter-term acceptance of risk. The field should be left blank for cases where a resolution is not possible/feasible and thus long-term risk acceptance is required.
15. If a POA&M Item has multiple milestones, each additional milestone must be entered as a separate row. For each milestone, the "Milestone Description", "Milestone Status", and "Milestone Scheduled Completion Date" are required. If the "Milestone Status" is set to 'Completed', then "Milestone Completion Date" is also required.
16. For unapproved POA&M Items, the "Milestone Scheduled Completion Date" cannot exceed that of the overall "Scheduled Completion Date". For POA&M Items that have a "Review Status" of 'Approved' in eMASS, a "Milestone Scheduled Completion Date" can be set beyond that of the overall "Scheduled Completion Date" to create a pending extension date.
17. To add a new milestone to an existing POA&M Item, insert a new row after the last existing milestone for the applicable POA&M. Information entered into that row will be used to populate the new milestone upon import.
18." Raw Severity" (optional field) can be populated with values of Very Low, Low, Moderate, High, or Very High. "Raw Severity" represents the initial or starting severity of the vulnerability prior to implementing mitigations and/or compensating Controls. Raw vulnerability ratings are typically determined by reviewing DISA publication guides, checklists, and/or databases from vulnerability scan engines.
19. Expected values for the optional fields of "Severity", "Relevance of Threat", "Likelihood", "Impact", and "Residual Risk Level" are 'Very Low', 'Low', 'Moderate', 'High', or 'Very High'.
20. If updating existing POA&M Item and/or milestone information, ensure that those changes are being applied to the latest version of each POA&M Item. Export the latest copy of applicable POA&M Items via the POA&M Import page in eMASS.