## POA&M
***** UNCLASSIFIED *****
Date Exported: |  |  | 09/24/2024 | [6 empty] | System Type: |  |  | OMB Project ID:
Exported By: |  |  | CHRIS RODRIGUEZ
CC/S/A/FA: | [9 empty] | POC Name: | CHRIS RODRIGUEZ
System / Project Name: | [9 empty] | POC Phone: | 760-685-7804 |  | Security Costs:
DoD IT Registration No: |  |  | N/A | [6 empty] | POC E-Mail: | CHRISTIAN.A.RODRIGUEZ@MANTECH.COM
| POA&M Item ID | Control Vulnerability Description | Controls / APs | Office/Org | Security Checks | Resources Required | Scheduled Completion Date | Milestone ID | Milestone with Completion Dates | Milestone Changes | Source Identifying Vulnerability | Status | Comments | Raw Severity | Devices Affected | Mitigations (in-house and in conjunction with the Navy CSSP) | Predisposing Conditions | Severity | Relevance of Threat | Threat Description | Likelihood | Impact | Impact Description | Residual Risk Level | Recommendations | Resulting Residual Risk after Proposed Mitigations
|  | POAM Description Field | CM-6.5 | NAVSEA, Chris Rodriguez, christian.a.rodriguez@mantech.com | V-219186 | Required Resources | 10/30/2024 | 1 | Milestone 1: Milestone Comments 1 Milestone Date: 09/21/2024 Milestone Status: Pending | Milestone 1 Changes: Change Comments 1 Milestone Date Change: 09/26/2024 Milestone Status: Pending | STIG Title | Ongoing | CCI-000366 Control mapping is unavailable for this vulnerability so it is being mapped to CM-6.5 CCI-000366 by default. Local Site Impact: Impact Description | Moderate |  | Mitigations | Predisposing Conditions | Moderate | High | ADVERSARIAL - HIGH: Per table D-2 Taxonomy of Threat Sources lists ADVERSARIAL as individual (outsider, insider, trusted insider, privileged insider), therefore the Relevance of Threat defaults to HIGH. | High | High |  | RedisualRisk | After reviewing documentation, and interviewing system stakeholders, it has been determined that this vulnerability should be mitigated. The ISSO will continue to monitor this vulnerability, and update the POAM as necessary. See mitigations field for detailed mitigation information. | Low
|  | POAM Description Field | CM-6.5 | NAVSEA, Chris Rodriguez, christian.a.rodriguez@mantech.com | V-219186 | Required Resources | 10/30/2024 | 1 | Milestone 1: Milestone Comments 1 Milestone Date: 09/21/2024 Milestone Status: Pending | Milestone 1 Changes: Change Comments 1 Milestone Date Change: 09/26/2024 Milestone Status: Pending | STIG Title | Ongoing | CCI-000366 Control mapping is unavailable for this vulnerability so it is being mapped to CM-6.5 CCI-000366 by default. Local Site Impact: Impact Description | Moderate |  | Mitigations | Predisposing Conditions | Moderate | High | ADVERSARIAL - HIGH: Per table D-2 Taxonomy of Threat Sources lists ADVERSARIAL as individual (outsider, insider, trusted insider, privileged insider), therefore the Relevance of Threat defaults to HIGH. | High | High |  | RedisualRisk | After reviewing documentation, and interviewing system stakeholders, it has been determined that this vulnerability should be mitigated. The ISSO will continue to monitor this vulnerability, and update the POAM as necessary. See mitigations field for detailed mitigation information. | Low
|  | POAM Description Field | CM-6.5 | NAVSEA, Chris Rodriguez, christian.a.rodriguez@mantech.com | V-219186 | Required Resources | 10/30/2024 | 1 | Milestone 1: Milestone Comments 1 Milestone Date: 09/21/2024 Milestone Status: Pending | Milestone 1 Changes: Change Comments 1 Milestone Date Change: 09/26/2024 Milestone Status: Pending | STIG Title | Ongoing | CCI-000366 Control mapping is unavailable for this vulnerability so it is being mapped to CM-6.5 CCI-000366 by default. Local Site Impact: Impact Description | Moderate |  | Mitigations | Predisposing Conditions | Moderate | High | ADVERSARIAL - HIGH: Per table D-2 Taxonomy of Threat Sources lists ADVERSARIAL as individual (outsider, insider, trusted insider, privileged insider), therefore the Relevance of Threat defaults to HIGH. | High | High |  | RedisualRisk | After reviewing documentation, and interviewing system stakeholders, it has been determined that this vulnerability should be mitigated. The ISSO will continue to monitor this vulnerability, and update the POAM as necessary. See mitigations field for detailed mitigation information. | Low
|  | POAM Description Field | CM-6.5 | NAVSEA, Chris Rodriguez, christian.a.rodriguez@mantech.com | V-219186 | Required Resources | 10/30/2024 | 1 | Milestone 1: Milestone Comments 1 Milestone Date: 09/21/2024 Milestone Status: Pending | Milestone 1 Changes: Change Comments 1 Milestone Date Change: 09/26/2024 Milestone Status: Pending | STIG Title | Ongoing | CCI-000366 Control mapping is unavailable for this vulnerability so it is being mapped to CM-6.5 CCI-000366 by default. Local Site Impact: Impact Description | Moderate |  | Mitigations | Predisposing Conditions | Moderate | High | ADVERSARIAL - HIGH: Per table D-2 Taxonomy of Threat Sources lists ADVERSARIAL as individual (outsider, insider, trusted insider, privileged insider), therefore the Relevance of Threat defaults to HIGH. | High | High |  | RedisualRisk | After reviewing documentation, and interviewing system stakeholders, it has been determined that this vulnerability should be mitigated. The ISSO will continue to monitor this vulnerability, and update the POAM as necessary. See mitigations field for detailed mitigation information. | Low
|  | POAM Description Field | CM-6.5 | NAVSEA, Chris Rodriguez, christian.a.rodriguez@mantech.com | V-219186 | Required Resources | 10/30/2024 | 1 | Milestone 1: Milestone Comments 1 Milestone Date: 09/21/2024 Milestone Status: Pending Milestone 2: Milestone Comments 2 Milestone Date: 09/21/2024 Milestone Status: Pending | Milestone 1 Changes: Change Comments 1 Milestone Date Change: 09/26/2024 Milestone Status: Pending Milestone 2 Changes: Change Comments 2 Milestone Date Change: 10/02/2024 Milestone Status: Pending | STIG Title | Ongoing | CCI-000366 Control mapping is unavailable for this vulnerability so it is being mapped to CM-6.5 CCI-000366 by default. Local Site Impact: Impact Description | Moderate |  | Mitigations | Predisposing Conditions | Moderate | High | ADVERSARIAL - HIGH: Per table D-2 Taxonomy of Threat Sources lists ADVERSARIAL as individual (outsider, insider, trusted insider, privileged insider), therefore the Relevance of Threat defaults to HIGH. | High | High |  | RedisualRisk | After reviewing documentation, and interviewing system stakeholders, it has been determined that this vulnerability should be mitigated. The ISSO will continue to monitor this vulnerability, and update the POAM as necessary. See mitigations field for detailed mitigation information. | Low
|  | 1234 | CM-6.5 | NAVSEA, Chris Rodriguez, christian.a.rodriguez@mantech.com | V-219186 |  | 06/06/2024 |  |  |  | Canonical Ubuntu 18.04 LTS Security Technical Implementation Guide | Ongoing | CCI-000366 Local Site Impact: Monitoring system files for changes against a baseline on a regular basis may help detect the possible introduction of malicious code on a system. | Moderate | Asset_Linux_0266 |  | 1 | Moderate | High | ADVERSARIAL - HIGH: Per table D-2 Taxonomy of Threat Sources lists ADVERSARIAL as individual (outsider, insider, trusted insider, privileged insider), therefore the Relevance of Threat defaults to HIGH. |  | High |  |  | After reviewing documentation, and interviewing system stakeholders, it has been determined that this vulnerability should be mitigated. The ISSO will continue to monitor this vulnerability, and update the POAM as necessary. See mitigations field for detailed mitigation information. | Low
|  | 1234 | IA-11.3 | NAVSEA, Chris Rodriguez, christian.a.rodriguez@mantech.com | V-214135 |  | 04/29/2024 |  |  |  | PostgreSQL 9.x Security Technical Implementation Guide | Ongoing | CCI-002038 Local Site Impact: Monitoring system files for changes against a baseline on a regular basis may help detect the possible introduction of malicious code on a system. | High | Asset_Linux_0269 |  |  | High | High | ADVERSARIAL - HIGH: Per table D-2 Taxonomy of Threat Sources lists ADVERSARIAL as individual (outsider, insider, trusted insider, privileged insider), therefore the Relevance of Threat defaults to HIGH. |  | High |  |  | After reviewing documentation, and interviewing system stakeholders, it has been determined that this vulnerability should be mitigated. The ISSO will continue to monitor this vulnerability, and update the POAM as necessary. See mitigations field for detailed mitigation information. | High
|  | 12345 | AU-3.1 | NAVSEA, Chris Rodriguez, christian.a.rodriguez@mantech.com | V-214138 |  | 05/14/2024 | 1 | Milestone 1: 7777 Milestone Date: 05/04/2024 Milestone Status: Pending |  | PostgreSQL 9.x Security Technical Implementation Guide | Ongoing | CCI-000130 Local Site Impact: Monitoring system files for changes against a baseline on a regular basis may help detect the possible introduction of malicious code on a system. | Moderate | Asset_Linux_0262 |  |  | Moderate | High | ADVERSARIAL - HIGH: Per table D-2 Taxonomy of Threat Sources lists ADVERSARIAL as individual (outsider, insider, trusted insider, privileged insider), therefore the Relevance of Threat defaults to HIGH. |  | High |  |  | After reviewing documentation, and interviewing system stakeholders, it has been determined that this vulnerability should be mitigated. The ISSO will continue to monitor this vulnerability, and update the POAM as necessary. See mitigations field for detailed mitigation information. | Moderate
|  | That's where she found herself and she didn't know what to do next. She asked the question even though she didn't really want to hear the answer. It was a no-win situation since she already knew. If he told the truth, she'd get confirmation of her worst fears. If he lied, she'd know that he wasn't who she thought he was which would be almost as bad. Yet she asked the question anyway and waited for his answer. He had done everything right. There had been no mistakes throughout the entire process. It had been perfection and he knew it without a doubt, but the results still stared back at him with the fact that he had lost. | AU-12.1 |  | V-214114 |  | 05/03/2024 |  |  |  | PostgreSQL 9.x Security Technical Implementation Guide | Ongoing | CCI-000169 Local Site Impact: Monitoring system files for changes against a baseline on a regular basis may help detect the possible introduction of malicious code on a system. | Moderate | Asset_Linux_0251 Asset_Linux_0269 |  |  | Moderate | High | ADVERSARIAL - HIGH: Per table D-2 Taxonomy of Threat Sources lists ADVERSARIAL as individual (outsider, insider, trusted insider, privileged insider), therefore the Relevance of Threat defaults to HIGH. |  | High |  |  | After reviewing documentation, and interviewing system stakeholders, it has been determined that this vulnerability should be mitigated. The ISSO will continue to monitor this vulnerability, and update the POAM as necessary. See mitigations field for detailed mitigation information. | Moderate
|  | When she heard the young boy's answer, she wondered if she had heard him correctly.It had been her dream for years but Dana had failed to take any action toward making it come true. There had always been a good excuse to delay or prioritize another project. As she woke, she realized she was once again at a crossroads. Would it be another excuse or would she finally find the courage to pursue her dream? Dana rose and took her first step.It was that terrifying feeling you have as you tightly hold the covers over you with the knowledge that there is something hiding under your bed. You want to look, but you don't at the same time. You're frozen with fear and unable to act. | AU-12.5 | NAVSEA, Chris Rodriguez, christian.a.rodriguez@mantech.com | V-219243 |  | 04/29/2024 |  |  |  | Canonical Ubuntu 18.04 LTS Security Technical Implementation Guide | Ongoing | CCI-000172 Local Site Impact: Monitoring system files for changes against a baseline on a regular basis may help detect the possible introduction of malicious code on a system. | High | Asset_Linux_0269 |  |  | High | High | ADVERSARIAL - HIGH: Per table D-2 Taxonomy of Threat Sources lists ADVERSARIAL as individual (outsider, insider, trusted insider, privileged insider), therefore the Relevance of Threat defaults to HIGH. |  | High |  |  | After reviewing documentation, and interviewing system stakeholders, it has been determined that this vulnerability should be mitigated. The ISSO will continue to monitor this vulnerability, and update the POAM as necessary. See mitigations field for detailed mitigation information. | High
|  | Not the standard hurry when you're in a rush to get someplace, but a frantic hurry. The type of hurry where a few seconds could mean life or death. She raced down the road ignoring speed limits and weaving between cars. She was only a few minutes away when traffic came to a dead standstill on the road ahead.She's asked the question so many times that she barely listened to the answers anymore. The answers were always the same. Well, not exactly the same, but the same in a general sense. A more accurate description was the answers never surprised her. So, she asked for the 10,000th time, "What's your favorite animal?" But this time was different. | AU-12.5 | NAVSEA, Chris Rodriguez, christian.a.rodriguez@mantech.com | V-214098 |  | 03/30/2024 | 1 | Milestone 1: 12345 Milestone Date: 03/19/2024 Milestone Status: Pending |  | PostgreSQL 9.x Security Technical Implementation Guide | Ongoing | CCI-000172 Local Site Impact: Monitoring system files for changes against a baseline on a regular basis may help detect the possible introduction of malicious code on a system. | High | Asset_Linux_0271 |  |  | High | High | ADVERSARIAL - HIGH: Per table D-2 Taxonomy of Threat Sources lists ADVERSARIAL as individual (outsider, insider, trusted insider, privileged insider), therefore the Relevance of Threat defaults to HIGH. |  | High |  |  | After reviewing documentation, and interviewing system stakeholders, it has been determined that this vulnerability should be mitigated. The ISSO will continue to monitor this vulnerability, and update the POAM as necessary. See mitigations field for detailed mitigation information. | High
|  | I sure hope that things get better soon. It was difficult to explain to them how the diagnosis of certain death had actually given him life. While everyone around him was in tears and upset, he actually felt more at ease. The doctor said it would be less than a year. That gave him a year to live, something he'd failed to do with his daily drudgery of a routine that had passed as life until then. One dollar and eighty-seven cents. That was all. And sixty cents of it was in pennies. Pennies saved one and two at a time by bulldozing the grocer and the vegetable man and the butcher until one’s cheeks burned with the silent imputation of parsimony that such close dealing implied. One dollar and eighty-seven cents. And the next day would be Christmas. She was in a hurry. | SC-8(2).2 | NAVSEA, Chris Rodriguez, christian.a.rodriguez@mantech.com | V-214073 |  | 04/30/2024 |  |  |  | PostgreSQL 9.x Security Technical Implementation Guide | Ongoing | CCI-002422 Local Site Impact: Monitoring system files for changes against a baseline on a regular basis may help detect the possible introduction of malicious code on a system. | High | Asset_Linux_0271 |  |  | High | High | ADVERSARIAL - HIGH: Per table D-2 Taxonomy of Threat Sources lists ADVERSARIAL as individual (outsider, insider, trusted insider, privileged insider), therefore the Relevance of Threat defaults to HIGH. |  | High |  |  | After reviewing documentation, and interviewing system stakeholders, it has been determined that this vulnerability should be mitigated. The ISSO will continue to monitor this vulnerability, and update the POAM as necessary. See mitigations field for detailed mitigation information. | High
|  | He latched onto them and their hate and couldn't let it go, but he also realized that this wasn't healthy. That's when he came up with his devious plan. He sat staring at the person in the train stopped at the station going in the opposite direction. She sat staring ahead, never noticing that she was being watched. Both trains began to move and he knew that in another timeline or in another universe, they had been happy together. There once lived an old man and an old woman who were peasants and had to work hard to earn their daily bread. The old man used to go to fix fences and do other odd jobs for the farmers around, and while he was gone the old woman, his wife, did the work of the house and worked in their own little plot of land. Things aren't going well at all with mom today. She is just a limp noodle and wants to sleep all the time. | CM-5(6).1 | NAVSEA, Chris Rodriguez, christian.a.rodriguez@mantech.com | V-214054 |  | 01/31/2024 |  |  |  | PostgreSQL 9.x Security Technical Implementation Guide | Ongoing | CCI-001499 Local Site Impact: Monitoring system files for changes against a baseline on a regular basis may help detect the possible introduction of malicious code on a system. | Low | Asset_Linux_0258 |  |  | Low | High | ADVERSARIAL - HIGH: Per table D-2 Taxonomy of Threat Sources lists ADVERSARIAL as individual (outsider, insider, trusted insider, privileged insider), therefore the Relevance of Threat defaults to HIGH. |  | High |  |  | After reviewing documentation, and interviewing system stakeholders, it has been determined that this vulnerability should be mitigated. The ISSO will continue to monitor this vulnerability, and update the POAM as necessary. See mitigations field for detailed mitigation information. | Low
|  | She had no desire to be there, but her mom had insisted that she go. She's resisted at first, but over time she realized it was simply easier to appease her and go. Mom tended to be that way. She would keep insisting until you wore down and did what she wanted. So, here she sat, patiently waiting for her number to be called. Sometimes it's simply better to ignore the haters. That's the lesson that Tom's dad had been trying to teach him, but Tom still couldn't let it go. | AU-12.5 |  | V-214087 |  | 01/31/2025 |  |  |  | PostgreSQL 9.x Security Technical Implementation Guide | Completed | CCI-000172 Local Site Impact: Monitoring system files for changes against a baseline on a regular basis may help detect the possible introduction of malicious code on a system. | Moderate | Asset_Linux_0268 |  |  | Moderate | High | ADVERSARIAL - HIGH: Per table D-2 Taxonomy of Threat Sources lists ADVERSARIAL as individual (outsider, insider, trusted insider, privileged insider), therefore the Relevance of Threat defaults to HIGH. |  | High |  |  | After reviewing documentation, and interviewing system stakeholders, it has been determined that this vulnerability should be mitigated. The ISSO will continue to monitor this vulnerability, and update the POAM as necessary. See mitigations field for detailed mitigation information. | Moderate
|  | I'd love to get together and tell you about it if you're up for a cup of coffee," he continued, laying the trap he'd been planning for years.Do you really listen when you are talking with someone? I have a friend who listens in an unforgiving way. She actually takes every word you say as being something important and when you have a friend that listens like that, words take on a whole new meaning.Sometimes that's just the way it has to be. Sure, there were probably other options, but he didn't let them enter his mind. It was done and that was that. It was just the way it had to be. | AC-10.1 | NAVSEA, Chris Rodriguez, christian.a.rodriguez@mantech.com | V-214059 |  | 12/31/2024 |  |  |  | PostgreSQL 9.x Security Technical Implementation Guide | Ongoing | CCI-000054 Local Site Impact: Monitoring system files for changes against a baseline on a regular basis may help detect the possible introduction of malicious code on a system. | High | Asset_Linux_0261 |  |  | High | High | ADVERSARIAL - HIGH: Per table D-2 Taxonomy of Threat Sources lists ADVERSARIAL as individual (outsider, insider, trusted insider, privileged insider), therefore the Relevance of Threat defaults to HIGH. |  | High |  |  | After reviewing documentation, and interviewing system stakeholders, it has been determined that this vulnerability should be mitigated. The ISSO will continue to monitor this vulnerability, and update the POAM as necessary. See mitigations field for detailed mitigation information. | High
|  | As she sat watching the world go by, something caught her eye. It wasn't so much its color or shape, but the way it was moving. She squinted to see if she could better understand what it was and where it was going, but it didn't help. As she continued to stare into the distance, she didn't understand why this uneasiness was building inside her body. She felt like she should get up and run. If only she could make out what it was. At that moment, she comprehended what it was and where it was heading, and she knew her life would never be the same.It was easy to spot her. All you needed to do was look at her socks. They were never a matching pair. One would be green while the other would be blue. One would reach her knee while the other barely touched her ankle. Every other part of her was perfect, but never the socks. They were her micro act of rebellion. "It was so great to hear from you today and it was such weird timing," he said. "This is going to sound funny and a little strange, but you were in a dream I had just a couple of days ago. | SC-13.2 |  | V-214117 |  | 06/30/2024 |  |  |  | PostgreSQL 9.x Security Technical Implementation Guide | Ongoing | CCI-002450 Local Site Impact: Monitoring system files for changes against a baseline on a regular basis may help detect the possible introduction of malicious code on a system. | High | Asset_Linux_0251 |  |  | High | High | ADVERSARIAL - HIGH: Per table D-2 Taxonomy of Threat Sources lists ADVERSARIAL as individual (outsider, insider, trusted insider, privileged insider), therefore the Relevance of Threat defaults to HIGH. |  | High |  |  | After reviewing documentation, and interviewing system stakeholders, it has been determined that this vulnerability should be mitigated. The ISSO will continue to monitor this vulnerability, and update the POAM as necessary. See mitigations field for detailed mitigation information. | High
|  | Well, not exactly the same, but the same in a general sense. A more accurate description was the answers never surprised her. So, she asked for the 10,000th time, "What's your favorite animal?" But this time was different. When she heard the young boy's answer, she wondered if she had heard him correctly.Cake or pie? I can tell a lot about you by which one you pick. It may seem silly, but cake people and pie people are really different. I know which one I hope you are, but that's not for me to decide. So, what is it? Cake or pie?MaryLou wore the tiara with pride. There was something that made doing anything she didn't really want to do a bit easier when she wore it. She really didn't care what those staring through the window were thinking as she vacuumed her apartment. | SI-11.1 |  | V-214053 |  | 07/16/2024 |  |  |  | PostgreSQL 9.x Security Technical Implementation Guide | Ongoing | CCI-001312 Local Site Impact: Monitoring system files for changes against a baseline on a regular basis may help detect the possible introduction of malicious code on a system. | Moderate | Asset_Linux_0275 |  |  | Moderate | High | ADVERSARIAL - HIGH: Per table D-2 Taxonomy of Threat Sources lists ADVERSARIAL as individual (outsider, insider, trusted insider, privileged insider), therefore the Relevance of Threat defaults to HIGH. |  | High |  |  | After reviewing documentation, and interviewing system stakeholders, it has been determined that this vulnerability should be mitigated. The ISSO will continue to monitor this vulnerability, and update the POAM as necessary. See mitigations field for detailed mitigation information. | Moderate

## Sheet1 (hidden)
Completed | Very Low | Very Low
Ongoing | Low | Low
Not Applicable | Moderate | Moderate
Archived | High | High
Risk Accepted | Very High | Very High
Navy_Standard

## 8500 IA Controls (hidden)
MAC I / CL | MAC I / S | MAC I / P | MAC II / CL | MAC II / S | MAC II / P | MAC III - CL | MAC III - S | MAC III - P | IA CONTROL | SUBJECT AREA | TITLE | IMPACT CODES
[6 empty] | Y | Y | Y | COAS-1 | Continuity | Alternate Site Designation | Medium
Y | Y | Y | Y | Y | Y |  |  |  | COAS-2 | Continuity | Alternate Site Designation | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | COBR-1 | Continuity | Protection of Backup and Restoration Assets | High
[6 empty] | Y | Y | Y | CODB-1 | Continuity | Data Backup Procedures | Low
|  |  | Y | Y | Y |  |  |  | CODB-2 | Continuity | Data Back-up Procedures | Medium
Y | Y | Y | [6 empty] | CODB-3 | Continuity | Data Backup Procedures | Medium
[6 empty] | Y | Y | Y | CODP-1 | Continuity | Disaster and Recovery Planning | Low
|  |  | Y | Y | Y |  |  |  | CODP-2 | Continuity | Disaster and Recovery Planning | Medium
Y | Y | Y | [6 empty] | CODP-3 | Continuity | Disaster and Recovery Planning | Medium
|  |  | Y | Y | Y | Y | Y | Y | COEB-1 | Continuity | Enclave Boundary Defense | Medium
Y | Y | Y | [6 empty] | COEB-2 | Continuity | Enclave Boundary Defense | High
|  |  | Y | Y | Y | Y | Y | Y | COED-1 | Continuity | Scheduled Exercises and Drills | Low
Y | Y | Y | [6 empty] | COED-2 | Continuity | Scheduled Exercises and Drills | Medium
[6 empty] | Y | Y | Y | COEF-1 | Continuity | Identification of Essential Functions | Low
Y | Y | Y | Y | Y | Y |  |  |  | COEF-2 | Continuity | Identification of Essential Functions | Medium
[6 empty] | Y | Y | Y | COMS-1 | Continuity | Maintenance Support | Low
Y | Y | Y | Y | Y | Y |  |  |  | COMS-2 | Continuity | Maintenance Support | Medium
[6 empty] | Y | Y | Y | COPS-1 | Continuity | Power Supply | Low
|  |  | Y | Y | Y |  |  |  | COPS-2 | Continuity | Power Supply | Medium
Y | Y | Y | [6 empty] | COPS-3 | Continuity | Power Supply | Medium
|  |  | Y | Y | Y | Y | Y | Y | COSP-1 | Continuity | Spares and Parts | Low
Y | Y | Y | [6 empty] | COSP-2 | Continuity | Spares and Parts | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | COSW-1 | Continuity | Backup Copies of Critical Software | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | COTR-1 | Continuity | Trusted Recovery | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | DCAR-1 | Security Design and Configuration | Procedural Review | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | DCAS-1 | Security Design and Configuration | Acquisition Standards | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | DCBP-1 | Security Design and Configuration | Best Security Practices | Medium
[6 empty] | Y | Y | Y | DCCB-1 | Security Design and Configuration | Control Board | Low
Y | Y | Y | Y | Y | Y |  |  |  | DCCB-2 | Security Design and Configuration | Control Board | Medium
[6 empty] | Y | Y | Y | DCCS-1 | Security Design and Configuration | Configuration Specifications | High
Y | Y | Y | Y | Y | Y |  |  |  | DCCS-2 | Security Design and Configuration | Configuration Specifications | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | DCCT-1 | Security Design and Configuration | Compliance Testing | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | DCDS-1 | Security Design and Configuration | Dedicated IA Services | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | DCFA-1 | Security Design and Configuration | Functional Architecture for AIS Applications | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | DCHW-1 | Security Design and Configuration | HW Baseline | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | DCID-1 | Security Design and Configuration | Interconnection Documentation | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | DCII-1 | Security Design and Configuration | IA Impact Assessment | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | DCIT-1 | Security Design and Configuration | IA for IT Services | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | DCMC-1 | Security Design and Configuration | Mobile Code | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | DCNR-1 | Security Design and Configuration | Non-repudiation | Medium
Y | Y | Y | Y | Y | Y |  |  |  | DCPA-1 | Security Design and Configuration | Partitioning the Application | Low
Y | Y | Y | Y | Y | Y |  |  |  | DCPB-1 | Security Design and Configuration | IA Program and Budget | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | DCPD-1 | Security Design and Configuration | Public Domain Software Controls | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | DCPP-1 | Security Design and Configuration | Ports, Protocols, and Services | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | DCPR-1 | Security Design and Configuration | CM Process | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | DCSD-1 | Security Design and Configuration | IA Documentation | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | DCSL-1 | Security Design and Configuration | System Library Management Controls | Medium
Y | Y | Y | Y | Y | Y |  |  |  | DCSP-1 | Security Design and Configuration | Security Support Structure Partitioning | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | DCSQ-1 | Security Design and Configuration | Software Quality | Medium
|  | Y |  |  | Y |  |  | Y | DCSR-1 | Security Design and Configuration | Specified Robustness - Basic | High
| Y |  |  | Y |  |  | Y |  | DCSR-2 | Security Design and Configuration | Specified Robustness - Medium | High
Y |  |  | Y |  |  | Y |  |  | DCSR-3 | Security Design and Configuration | Specified Robustness – High | High
[7 empty] | Y | Y | DCSS-1 | Security Design and Configuration | System State Changes | High
Y | Y | Y | Y | Y | Y | Y |  |  | DCSS-2 | Security Design and Configuration | System State Changes | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | DCSW-1 | Security Design and Configuration | SW Baseline | High
|  | Y |  |  | Y |  |  | Y | EBBD-1 | Enclave and Computing Environment | Boundary Defense | Low
| Y |  |  | Y |  |  | Y |  | EBBD-2 | Enclave and Computing Environment | Boundary Defense | Medium
Y |  |  | Y |  |  | Y |  |  | EBBD-3 | Enclave and Computing Environment | Boundary Defense | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | EBCR-1 | Enclave and Computing Environment | Connection Rules | Medium
| Y | Y |  | Y | Y |  | Y | Y | EBPW-1 | Enclave and Computing Environment | Public WAN Connection | High
Y | Y |  | Y | Y |  | Y | Y |  | EBRP-1 | Enclave and Computing Environment | Remote Access for Privileged Functions | High
Y | Y |  | Y | Y |  | Y | Y |  | EBRU-1 | Enclave and Computing Environment | Remote Access for User Functions | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | EBVC-1 | Enclave and Computing Environment | VPN Controls | Medium
Y | Y |  | Y | Y |  | Y | Y |  | ECAD-1 | Enclave and Computing Environment | Affiliation Display | Medium
Y | Y |  | Y | Y |  | Y | Y |  | ECAN-1 | Enclave and Computing Environment | Access for Need-to-Know | High
|  | Y |  |  | Y |  |  | Y | ECAR-1 | Enclave and Computing Environment | Audit Record Content | Low
| Y |  |  | Y |  |  | Y |  | ECAR-2 | Enclave and Computing Environment | Audit Record Content | Medium
Y |  |  | Y |  |  | Y |  |  | ECAR-3 | Enclave and Computing Environment | Audit Record Content | High
[7 empty] | Y | Y | ECAT-1 | Enclave and Computing Environment | Audit Trail, Monitoring, Analysis and Reporting | Low
Y | Y | Y | Y | Y | Y | Y |  |  | ECAT-2 | Enclave and Computing Environment | Audit Trail, Monitoring, Analysis and Reporting | Medium
[7 empty] | Y | Y | ECCD-1 | Enclave and Computing Environment | Changes to Data | Medium
Y | Y | Y | Y | Y | Y | Y |  |  | ECCD-2 | Enclave and Computing Environment | Changes to Data | High
Y |  |  | Y |  |  | Y |  |  | ECCM-1 | Enclave and Computing Environment | COMSEC | High
| Y |  |  | Y |  |  | Y |  | ECCR-1 | Enclave and Computing Environment | Encryption for Confidentiality (Data at Rest) | Low
Y |  |  | Y |  |  | Y |  |  | ECCR-2 | Enclave and Computing Environment | Encryption for Confidentiality (Data at Rest) | Medium
Y |  |  | Y |  |  | Y |  |  | ECCR-3 | Enclave and Computing Environment | Encryption for Confidentiality (Data at Rest) | High
| Y |  |  | Y |  |  | Y |  | ECCT-1 | Enclave and Computing Environment | Encryption for Confidentiality (Data in Transit) | Medium
Y |  |  | Y |  |  | Y |  |  | ECCT-2 | Enclave and Computing Environment | Encryption for Confidentiality (Data in Transit) | High
Y | Y | Y | Y | Y | Y |  |  |  | ECDC-1 | Enclave and Computing Environment | Data Change Controls | Medium
Y | Y |  | Y | Y |  | Y | Y |  | ECIC-1 | Enclave and Computing Environment | Interconnection among DoD Systems and Enclaves | Medium
Y | Y | Y | Y | Y | Y |  |  |  | ECID-1 | Enclave and Computing Environment | Host Based IDS | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | ECIM-1 | Enclave and Computing Environment | Instant Messaging | Medium
Y |  |  | Y |  |  | Y |  |  | ECLC-1 | Enclave and Computing Environment | Audit of Security Label Changes | Low
| Y |  |  | Y |  |  | Y |  | ECLO-1 | Enclave and Computing Environment | Logon | Medium
Y |  |  | Y |  |  | Y |  |  | ECLO-2 | Enclave and Computing Environment | Logon | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | ECLP-1 | Enclave and Computing Environment | Least Privilege | High
Y | Y |  | Y | Y |  | Y | Y |  | ECML-1 | Enclave and Computing Environment | Marking and Labeling | High
| Y | Y |  | Y | Y |  | Y | Y | ECMT-1 | Enclave and Computing Environment | Conformance Monitoring and Testing | Low
Y |  |  | Y |  |  | Y |  |  | ECMT-2 | Enclave and Computing Environment | Conformance Monitoring and Testing | Medium
[6 empty] | Y | Y | Y | ECND-1 | Enclave and Computing Environment | Network Device Controls | Low
Y | Y | Y | Y | Y | Y |  |  |  | ECND-2 | Enclave and Computing Environment | Network Device Controls | Medium
Y | Y |  | Y | Y |  | Y | Y |  | ECNK-1 | Enclave and Computing Environment | Encryption for Need-To-Know | Medium
Y |  |  | Y |  |  | Y |  |  | ECNK-2 | Enclave and Computing Environment | Encryption for Need-To-Know | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | ECPA-1 | Enclave and Computing Environment | Privileged Account Control | High
[6 empty] | Y | Y | Y | ECPC-1 | Enclave and Computing Environment | Production Code Change Controls | Medium
Y | Y | Y | Y | Y | Y |  |  |  | ECPC-2 | Enclave and Computing Environment | Production Code Change Controls | Medium
Y | Y |  | Y | Y |  | Y | Y |  | ECRC-1 | Enclave and Computing Environment | Resource Control | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | ECRG-1 | Enclave and Computing Environment | Audit Reduction and Report Generation | Low
Y | Y | Y | Y | Y | Y | Y | Y | Y | ECRR-1 | Enclave and Computing Environment | Audit Record Retention | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | ECSC-1 | Enclave and Computing Environment | Security Configuration Compliance | High
[6 empty] | Y | Y | Y | ECSD-1 | Enclave and Computing Environment | Software Development Change Controls | Medium
Y | Y | Y | Y | Y | Y |  |  |  | ECSD-2 | Enclave and Computing Environment | Software Development Change Controls | High
Y | Y | Y | Y | Y | Y | Y |  |  | ECTB-1 | Enclave and Computing Environment | Audit Trail Backup | Medium
Y | Y |  | Y | Y |  | Y | Y |  | ECTC-1 | Enclave and Computing Environment | Tempest Controls | High
[6 empty] | Y | Y | Y | ECTM-1 | Enclave and Computing Environment | Transmission Integrity Controls | Medium
Y | Y | Y | Y | Y | Y |  |  |  | ECTM-2 | Enclave and Computing Environment | Transmission Integrity Controls | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | ECTP-1 | Enclave and Computing Environment | Audit Trail Protection | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | ECVI-1 | Enclave and Computing Environment | Voice over IP | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | ECVP-1 | Enclave and Computing Environment | Virus Protection | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | ECWM-1 | Enclave and Computing Environment | Warning Message | Low
Y | Y | Y | Y | Y | Y | Y | Y | Y | ECWN-1 | Enclave and Computing Environment | Wireless Computing and Networking | High
Y | Y |  | Y | Y |  | Y | Y |  | IAAC-1 | Enclave and Computing Environment | Account Control | High
Y | Y |  | Y | Y |  | Y | Y |  | IAGA-1 | Identification and Authentication | Group Identification and Authentication | Medium
| Y |  |  | Y |  |  | Y |  | IAIA-1 | Identification and Authentication | Individual Identification and Authentication | High
Y |  |  | Y |  |  | Y |  |  | IAIA-2 | Identification and Authentication | Individual Identification and Authentication | High
[7 empty] | Y | Y | IAKM-1 | Identification and Authentication | Key Management | Medium
| Y | Y |  | Y | Y |  |  |  | IAKM-2 | Identification and Authentication | Key Management | Medium
Y |  |  | Y |  |  | Y |  |  | IAKM-3 | Identification and Authentication | Key Management | Medium
[6 empty] | Y | Y | Y | IATS-1 | Identification and Authentication | Token and Certificate Standards | Medium
Y | Y | Y | Y | Y | Y |  |  |  | IATS-2 | Identification and Authentication | Token and Certificate Standards | Medium
| Y |  |  | Y |  |  | Y |  | PECF-1 | Physical and Environmental | Access to Computing Facilities | High
Y |  |  | Y |  |  | Y |  |  | PECF-2 | Physical and Environmental | Access to Computing Facilities | High
| Y |  |  | Y |  |  | Y |  | PECS-1 | Physical and Environmental | Clearing and Sanitizing | High
Y |  |  | Y |  |  | Y |  |  | PECS-2 | Physical and Environmental | Clearing and Sanitizing | High
Y |  |  | Y |  |  | Y |  |  | PEDD-1 | Physical and Environmental | Destruction | High
Y | Y |  | Y | Y |  | Y | Y |  | PEDI-1 | Physical and Environmental | Data Interception | High
[6 empty] | Y | Y | Y | PEEL-1 | Physical and Environmental | Emergency Lighting | Low
Y | Y | Y | Y | Y | Y |  |  |  | PEEL-2 | Physical and Environmental | Emergency Lighting | Medium
[6 empty] | Y | Y | Y | PEFD-1 | Physical and Environmental | Fire Detection | High
Y | Y | Y | Y | Y | Y |  |  |  | PEFD-2 | Physical and Environmental | Fire Detection | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | PEFI-1 | Physical and Environmental | Fire Inspection | Medium
[6 empty] | Y | Y | Y | PEFS-1 | Physical and Environmental | Fire Suppression System | Medium
Y | Y | Y | Y | Y | Y |  |  |  | PEFS-2 | Physical and Environmental | Fire Suppression System | High
[6 empty] | Y | Y | Y | PEHC-1 | Physical and Environmental | Humidity Controls | Medium
Y | Y | Y | Y | Y | Y |  |  |  | PEHC-2 | Physical and Environmental | Humidity Controls | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | PEMS-1 | Physical and Environmental | Master Power Switch | High
| Y |  |  | Y |  |  | Y |  | PEPF-1 | Physical and Environmental | Physical Protection of Facilities | High
Y |  |  | Y |  |  | Y |  |  | PEPF-2 | Physical and Environmental | Physical Protection of Facilities | High
Y | Y |  | Y | Y |  | Y | Y |  | PEPS-1 | Physical and Environmental | Physical Security Testing | Low
Y | Y | Y | Y | Y | Y | Y | Y | Y | PESL-1 | Physical and Environmental | Screen Lock | Medium
Y | Y |  | Y | Y |  | Y | Y |  | PESP-1 | Physical and Environmental | Workplace Security Procedures | Medium
Y | Y |  | Y | Y |  | Y | Y |  | PESS-1 | Physical and Environmental | Storage | High
[6 empty] | Y | Y | Y | PETC-1 | Physical and Environmental | Temperature Controls | Low
Y | Y | Y | Y | Y | Y |  |  |  | PETC-2 | Physical and Environmental | Temperature Controls | Medium
Y | Y | Y | Y | Y | Y | Y | Y | Y | PETN-1 | Physical and Environmental | Environmental Control Training | Low
Y | Y |  | Y | Y |  | Y | Y |  | PEVC-1 | Physical and Environmental | Visitor Control to Computing Facilities | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | PEVR-1 | Physical and Environmental | Voltage Regulators | High
| Y |  |  | Y |  |  | Y |  | PRAS-1 | Personnel | Access to Information | High
Y |  |  | Y |  |  | Y |  |  | PRAS-2 | Personnel | Access to Information | High
| Y | Y |  | Y | Y |  | Y | Y | PRMP-1 | Personnel | Maintenance Personnel | High
Y |  |  | Y |  |  | Y |  |  | PRMP-2 | Personnel | Maintenance Personnel | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | PRNK-1 | Personnel | Access to Need-to-Know Information | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | PRRB-1 | Personnel | Security Rules of Behavior or Acceptable Use Policy | High
Y | Y |  | Y | Y |  | Y | Y |  | PRTN-1 | Personnel | Information Assurance Training | High
|  |  | Y | Y | Y | Y | Y | Y | VIIR-1 | Vulnerabiity and Incident Management | Incident Response Planning | Medium
Y | Y | Y | [6 empty] | VIIR-2 | Vulnerabiity and Incident Management | Incident Response Planning | High
Y | Y | Y | Y | Y | Y | Y | Y | Y | VIVM-1 | Vulnerabiity and Incident Management | Vulnerability Management | Medium
110 | 106 | 81 | 110 | 106 | 81 | 105 | 100 | 75

## Example
***** CONTROLLED UNCLASSIFIED INFORMATION *****
Date Exported: |  |  | 2/20/2018 | [6 empty] | System Type: | IS Enclave |  | OMB Project ID: | 54324
Exported By: |  |  | John Smith
CC/S/A/FA: |  |  | DoD | [6 empty] | POC Name: | John Smith
System / Project Name: |  |  | First System | [6 empty] | POC Phone: | 747-380-0987 |  | Security Costs: | 10000
DoD IT Registration No: |  |  | 5050 | [6 empty] | POC E-Mail: | john.smith@mail.mil
| POA&M Item ID | Control Vulnerability Description | Controls / APs | Office/Org | Security Checks | Resources Required | Scheduled Completion Date | Milestone ID | Milestone with Completion Dates | Milestone Changes | Source Identifying Vulnerability | Status | Comments | Raw Severity | Devices Affected | Mitigations (in-house and in conjunction with the Navy CSSP) | Predisposing Conditions | Severity | Relevance of Threat | Threat Description | Likelihood | Impact | Impact Description | Residual Risk Level | Recommendations | Resulting Residual Risk after Proposed Mitigations
| 1 | Description that explains the identified vulnerability and any other pertinent information. | AC-1 | DoD, John Smith, 7033775472, smith_john@email.com | SV-18394r2_rule | Resources required to correct the identified vulnerability. | 2018-11-23 | 1 | Implement Procedure A 10/25/2018 |  | Narrative description of how this vulnerability was discovered (annual review, automated scan, etc.) | Ongoing | Description of any relevant information not captured by the other fields. | High | Identify affected devices. | Description of the mitigations in place (if any) to counter this vulnerability. | Description of the predisposing conditions (if any). | High | High | Description of the identified theat(s). | High | High | Description of magnitude of potential harm from the exploitation of this vulnerability. | High | Summary of the recommended actions that will further address/reduce the risk of this vulnerability. | Moderate
[8 empty] | 2 | Implement Procedure B 10/31/2018
[8 empty] | 3 | Implement Procedure C 11/5/2018
| 2 | Description that explains the identified vulnerability and any other pertinent information. | SA-1.4 | DoD | SV-40098r2_rule | Resources required to correct the identified vulnerability. |  |  |  |  | Narrative description of how this vulnerability was discovered (annual review, automated scan, etc.) | Risk Accepted | Description of any relevant information not captured by the other fields. | Low | Identify affected devices. | Description of the mitigations in place (if any) to counter this vulnerability. | Description of the predisposing conditions (if any). | Very Low | Low | Description of the identified theat(s). | Very Low | Moderate | Description of magnitude of potential harm from the exploitation of this vulnerability. | Low | Summary of the recommended actions that will further address/reduce the risk of this vulnerability. | Very Low
| 3 | Description that explains the identified vulnerability and any other pertinent information. |  | Example Program Management Office |  | Resources required to correct the identified vulnerability. | 2018-10-25 | 4 | Description of Milestone 10/17/2018 | Updated Milestone Description 10/22/2018 | Narrative description of how this vulnerability was discovered (annual review, automated scan, etc.) | Completed 11/13/2018 | Description of any relevant information not captured by the other fields. | Low | Identify affected devices. | Description of the mitigations in place (if any) to counter this vulnerability. | Description of the predisposing conditions (if any). | High | Moderate | Description of the identified theat(s). | Moderate | High | Description of magnitude of potential harm from the exploitation of this vulnerability. | Moderate | Summary of the recommended actions that will further address/reduce the risk of this vulnerability. | Low

## Instructions
POA&M Template Instructions
1. Enter valid information into the fields on the POA&M Template.
2. The POA&M Item ID and Milestone ID are automatically generated by eMASS after the POA&M Item is successfully imported. No user action is required to complete or update and therefore these columns can be treated as read-only.
3. Control Vulnerability Description - Describe the vulnerability associated with each non-compliant security control. This should be the test tool defined vulnerability description.
4. Controls / APs - List the affected security controls / assessment procedures.
5. Office/Org - When entering Office/Org, enter Organization, First Name Last Name, Phone Number, Email. At a minimum, the Office/Org must be defined for each POA&M Item. If multiple fields are entered, ensure each field is separated by a comma. Do not separate first and last name with a comma.
6. Security Checks - NIST -53Rev 4 Assessment Procedure, STIG / SRG Vulnerability ID, or ACAS Plugin ID (Do not leave this field blank).
7. Resources Required - What resources are required in order to address the vulnerability.
8. Scheduled Completion Date - When does the program anticipate remediating the vulnerability.
9. Milestone with Completion Dates - List milestones and completions dates. If a POA&M Item has multiple milestones, each milestone must be entered in separate rows within the Milestone w/Completion Date field.
10. Milestone Changes - List any milestone changes / deviations. If a POA&M Item has multiple milestone changes, each milestone change must be entered chronologically in separate rows within the Milestone Changes field.
11. Source Identifying Vulnerability - NIST 800-53Rev4 AP, STIG (List STIG name), ACAS. Note: Mark as appropriate for other discovery sources - i.e. Web Risk Assessment, CSI findings not tied to standard tools, etc.
12. Status - N/A, Ongoing, Completed. Note: Risk Accepted should only be selected once the AO has accepted the risk.
13. Comments - Add any additional feedback not covered in specific POA&M fields.
14. Raw Severity - Record the initial severity as identified by the test methodology. Failed 800-53 R4 assessment procedures without clearly identified severity/impact should assume the high watermark of the C-I-A impact to the parent control (e.g, a failed assessment procedure affecting Integrity for a system with Moderate impact to Integrity would assume a Moderate raw test result).
15. Devices Affected - List affected devices (by hostname). Devices of varying configuration and purpose may be impacted differently by a vulnerability and should be listed as separate line items in the RAR for risk analysis.
16. Mitigations (in-house and in conjunction with the Navy CSSP) - Technical mitigation(s) that are present and further reduce the initial severity. Enter "none" if there is no applied mitigation that decreases severity/pervasiveness. Mitigations directly address the vulnerability and are compensating countermeasures. (e.g. custom HBSS signature preventing execution of a specific vulnerable .dll on a system, failover or redundancy addressing DoS conditions) in accordance with the Navy Certifying Authority Mitigation Methodology memorandum dated 01 Oct 2014.
17. Predisposing Conditions - Predisposing condition(s) that affect the raw severity value. Enter "none" if there is no relevant condition that increases or decreases severity/pervasiveness. A predisposing condition is a condition existing within an organization, a mission or business process, enterprise architecture, information system/PIT, or environment of operation, which affects (i.e., increases or decreases) the likelihood that threat events, once initiated, result in adverse impacts. (Department of Defense (DoD) Cybersecurity Risk Assessment Guide, page 4)
18. Severity - Vulnerability severity is derived from the raw vulnerability, adjusted by relevant predisposing conditions and mitigations. If there are no relevant predisposing conditions or applied technical mitigation(s), the severity aligns with the raw test results. Identify the severity or pervasiveness as one of the following: Very Low (VL) Low (L) Moderate (M) High (H) Very High (VH)
19. Relevance of Threat - Determine whether the threat source is adversarial or non-adversarial in nature. Adversarial threat source: the DoD Risk Assessment Guide notes the significance of the "advanced persistent threat". Vulnerabilities of an adversarial nature must reflect a minimum of "High" in this field. Non-adversarial threat source: This value takes into consideration multiple NIST SP 800-30 risk factors, such as the range of effects, extent of resources affected and whether any critical resources are affected; Relevance of Threat descriptions from the NIST SP 800-30 are included in the "Assessment Tables" tab in Table D-2. Identify the relevance of threat as one of the following: Very Low (VL) - minimal effects involving few, if any resources, involving no critical resources Low (L) - limited effects involving some resources, involving no critical resources Moderate (M) - wide-ranging effects involving a significant portion of resources, including some critical resources High (H) - extensive effects involving most resources, including many critical resources Very High (VH) - sweeping effects involving almost all resources
20. Threat Description - Enter description supporting the value listed in the Relevance of Threat field. Identify adversarial vs. non-adversarial; for non-adversarial, identify portion of resources affected and whether any critical resources are affected. Note: If adequate justification is not provided, the Relevance of Threat will default to "High".
21. Likelihood - Note: This value is automatically calculated as a result of "Severity" and "Relevance of Threat". DO NOT CHANGE THE RECOMMENDED VALUE. Determine the likelihood a threat event will be initiated or occur and result in adverse impacts (see Table 5 on the RMF KS page "Model for Assessing Residual Risk Level for Non-Compliant Security Controls" for likelihood values). Likelihood is a combination of likelihood of attack initiation / occurrence and likelihood that initiated attack succeeds or the threat even results in adverse impact. If resource constraints allow, risk assessors may reference NIST SP 800-30 for guidance on determining this value (i.e., could use another 5x5 matrix to plot the two factors and determine the overall likelihood). However, as the likelihood is summarized in this model, risk assessors assign a value by comparing the results of "Severity" with the "Relevance of Threat." The factors from these two columns are plotted on a 5x5 matrix, and the intersection on the matrix indicates the value for likelihood. Identify the likelihood as one of the following: Very Low (VL) Low (L) Moderate (M) High (H) Very High (VH)
22. Impact - Determine the adverse impact (i.e., potential harm to organizational operations, organizational assets, individuals, other organizations, or the Nation) from the threat event. Risk assessors may consider the Concept of Operations, system description, User Representative input, etc. (See Table 6 on the RMF KS page "Model for Assessing Residual Risk Level for Non-Compliant Security Controls" for descriptions of the values assigned to impact. Identify the impact as one of the following: Very Low (VL) Low (L) Moderate (M) High (H) Very High (VH)
23. Impact Description - Describe the impact to the mission, information system, organization and organizational assets, other organizations, individuals, or the Nation as a result of exploitation of the vulnerability/weakness. Note: If adequate justification is not provided, the Impact will default to a minimum of "High".
24. Residual Risk Level - Note: This value is automatically calculated as a result of "Likelihood" and "Impact" fields. DO NOT CHANGE THE RECOMMENDED VALUE. Determine the level of risk as a combination of likelihood and impact (see Table 7 on the RMF KS page "Model for Assessing Residual Risk Level for Non-Compliant Security Controls" for descriptions of values assigned to risk). Identify the risk as one of the following: Very Low (VL) Low (L) Moderate (M) High (H) Very High (VH)
25. Recommendations - The PM/SM lists the recommendations addressing actions that will at a minimum reduce the High and Very High Risk non-compliant security controls to a Moderate Risk.
26. Resulting Residual Risk after Proposed Mitigations - Indicate the risk level expected after the proposed mitigations are implemented.
Situational Awareness
1. To import a System-level POA&M Item, the Controls / APs field must be left blank.
2. To import a Control-level POA&M Item, enter the appropriate Control / Assessment Procedure Acronym(s) (e.g., AC-3) into the Controls / APs field.
3. When listing multiple Control / Assessment Procedure Associations for a specific POA&M item, separate each association by a semicolon.
4. For unapproved POA&M Items, the Milestone Scheduled Completion Date cannot exceed that of the overall Scheduled Completion Date. For POA&M Items that have a Review Status of "Approved" in eMASS, a Milestone Scheduled Completion Date can be set beyond that of the overall Scheduled Completion Date to create a pending Extension Date.
5. Dates in the Status (for Completed & AO Approved Risk Accepted POA&M Items), Milestones w/Completion Dates, and Milestone Changes fields must be entered after text.
6. Values for the optional fields of Impact and Residual Risk Level should be reflective of the DoD-defined risk calculation matrixes in Tables 8 and 9 on the RMF Knowledge Service (https://rmfks.osd.mil/rmf/RMFImplementation/AssessControls/Pages/ResidualRisk.aspx).
7. Do not delete columns/sheets, delete the classification label, or add additional columns. Doing so may have a negative impact on the ability for eMASS to ingest the template.
8. To add a new milestone to an existing POA&M Item, insert a new row after the last existing milestone for the applicable POA&M. Information entered into that row will be used to populate the new milestone upon import. The Milestone ID column for a new milestone can be left blank and will be automatically created by eMASS upon import.
Combination of Vulnerability Severity/Predisposing Condition Pervasiveness and Threat Relevance
| Relevance of Threat | Vulnerability Severity/Predisposing Condition Pervasiveness
|  | Very Low | Low | Moderate | High | Very High
| Very High | Very Low | Low | Moderate | High | Very High
| High | Very Low | Low | Moderate | High | Very High
| Moderate | Very Low | Low | Moderate | Moderate | High
| Low | Very Low | Low | Low | Low | Moderate
| Very Low | Very Low | Very Low | Low | Low | Low
Combination of Likelihood and Impact
| Likelihood (Threat Event Occurs and Results in Adverse Impact) | Impact
|  | Very Low | Low | Moderate | High | Very High
| Very High | Very Low | Low | Moderate | High | Very High
| High | Very Low | Low | Moderate | High | Very High
| Moderate | Very Low | Low | Moderate | Moderate | High
| Low | Very Low | Low | Low | Low | Moderate
| Very Low | Very Low | Very Low | Low | Low | Low